## Summary
Handover checklist — com.ilyassavli.helloworld
Generated 2026-10-16 by android-engineer. Refresh: python3 tools/handover_check.py (keeps the statuses and notes you entered).
Status | Actions
To do | 11
Done | 1
N/A | 0
Release blockers open | 5
Open by owner | Actions
Backend | 1
DevOps | 5
Developer | 2
Product | 3
Release blockers (do these before the first Play upload) |  | Owner
SIGN-1 — Create the release keystore |  | DevOps
SIGN-2 — Add the signing secrets to GitHub |  | DevOps
STORE-1 — Replace the placeholder app icon |  | Product
STORE-2 — Create the Play Console app and store listing |  | Product
STORE-3 — Fill in the Data safety form |  | Product

## Actions
ID | Area | Task | Why | How | Owner | Release blocker | Verify | Status | Notes
SIGN-1 | Release signing | Create the release keystore | Play only accepts builds signed with your upload key; the project never stores a keystore. | 1. keytool -genkeypair -v -keystore release.jks -alias upload -keyalg RSA -keysize 4096 -validity 10000 2. Store release.jks and both passwords in your password manager (losing them blocks future updates). 3. Enrol in Play App Signing when creating the app (STORE-2). | DevOps | Yes | KEYSTORE_PATH=… ./gradlew :app:bundleProdRelease, then: apksigner verify --print-certs on an APK from the bundle | To do
SIGN-2 | Release signing | Add the signing secrets to GitHub | The release workflow (release-artifact.yml or release-play.yml) and the test-build workflows sign only when these secrets exist (HARD-07). | GitHub → repo → Settings → Secrets and variables → Actions → New repository secret: KEYSTORE_BASE64 = output of: base64 -i release.jks KEYSTORE_PASSWORD, KEY_ALIAS, KEY_PASSWORD | DevOps | Yes | Push a v* tag → the Release workflow uploads release-aab | To do
CI-1 | CI | Add NVD_API_KEY for the dependency scan | dependency-scan.yml (OWASP) fails or is extremely slow without an NVD API key (HARD-08). | 1. Request a free key at https://nvd.nist.gov/developers/request-an-api-key 2. Add it as the GitHub secret NVD_API_KEY. | DevOps | No | Actions → Dependency scan → Run workflow succeeds | To do
CI-2 | CI | Protect main and require the CI check | The rules are only enforced for humans if a red CI blocks merging (CI-01). | GitHub → Settings → Branches → Add rule for main: require a pull request, require status check 'verify' (CI workflow), block force-pushes. | DevOps | No | Open a PR with a failing test → merge is blocked | To do
STORE-1 | Store | Replace the placeholder app icon | The template ships a placeholder launcher glyph. | Android Studio → New → Image Asset (adaptive + monochrome) → replace app/src/main/res/drawable/ic_launcher_foreground.xml and the ic_launcher_background color. | Product | Yes | Install the app: the launcher shows the real icon (also in themed-icons mode) | To do | auto: placeholder icon still in place
STORE-2 | Store | Create the Play Console app and store listing | Needed before the first upload: listing, content rating, target audience, privacy policy URL. | Play Console → Create app (package com.ilyassavli.helloworld) → Store listing, App content (content rating, target audience, privacy policy, ads), enable Play App Signing. | Product | Yes | Upload the AAB to the internal testing track without errors | To do
STORE-3 | Store | Fill in the Data safety form | Required by Play; must list what the app and its SDKs collect (no third-party analytics SDKs). | Play Console → App content → Data safety. Use each SDK's data-safety guidance; declare encryption in transit (HTTPS only). | Product | Yes | Data safety section shows 'Completed' | To do
STORE-4 | Store | Set the release version | versionCode must grow with every upload; the build reads it from Gradle properties. | CI or local: ./gradlew :app:bundleProdRelease -Papp.versionCode=<n> -Papp.versionName=<x.y.z> | Developer | No | aapt2 dump badging shows the expected versionCode | To do
ENV-1 | Environments | Provide the stage environment | The stage flavor (com.ilyassavli.helloworld.stage) talks to api.stage.baseUrl and installs next to prod. | Make sure the stage backend exists and set api.stage.baseUrl / api.stage.certPins. Register com.ilyassavli.helloworld.stage wherever the prod package is registered (Firebase, deep links, OAuth). | Backend | No | installStageDebug shows 'Stage' in the app name and loads data | To do
DIST-1 | Delivery | Set up Firebase App Distribution for CI | distribute-firebase.yml uploads the stage release build to testers with a service account. | 1. Google Cloud console (the Firebase project) → IAM → service account with the role 'Firebase App Distribution Admin' → JSON key → GitHub secret FIREBASE_SERVICE_ACCOUNT_JSON. 2. Firebase console → App Distribution → Testers & Groups → group 'testers' with the testers' emails. | DevOps | No | Push to main (or run the workflow by hand) → testers get an email with the new build | To do
DIST-FB-1 | Delivery | Add the Firebase app id for App Distribution | The upload fails with 'Missing app id' until gradle.properties has it (it is not a secret). | Firebase console → Project settings → Your apps → the Android app com.ilyassavli.helloworld.stage (single environment: com.ilyassavli.helloworld) → App ID (1:…:android:…) → gradle.properties: firebase.stage.appId= (single environment: firebase.appId=). | DevOps | No | python3 tools/handover_check.py shows this item as Done | Done | auto: app id set
DIST-LOCAL-1 | Delivery | Back up the local upload keystore | tools/export_build.sh --create-keystore keeps the key in ~/.android-keystores and its passwords in ~/.gradle/gradle.properties — outside the repo. Losing it blocks app updates. | Copy ~/.android-keystores/<project>.jks and the <project>.keystore.* lines from ~/.gradle/gradle.properties into the team's password manager. For CI, base64 it into KEYSTORE_BASE64 with the same passwords. | Developer | No | The backup restores and tools/export_build.sh signs with it | To do

## Secrets & keys
Name | What it is | Where it goes | Flavor | How to get it | Read by
KEYSTORE_BASE64 | Base64 of the release/upload keystore | GitHub secret | prod | base64 -i release.jks | .github/workflows/release-artifact.yml or release-play.yml (+ distribute-*.yml)
KEYSTORE_PASSWORD | Keystore password | GitHub secret | prod | Password manager (SIGN-1) | app/build.gradle.kts (env)
KEY_ALIAS | Key alias (e.g. upload) | GitHub secret | prod | From SIGN-1 | app/build.gradle.kts (env)
KEY_PASSWORD | Key password | GitHub secret | prod | Password manager (SIGN-1) | app/build.gradle.kts (env)
NVD_API_KEY | NVD API key for OWASP dependency-check | GitHub secret | — | nvd.nist.gov developer key | .github/workflows/dependency-scan.yml
FIREBASE_SERVICE_ACCOUNT_JSON | Service account JSON (App Distribution Admin) | GitHub secret | stage | Google Cloud console → IAM → service account key | .github/workflows/distribute-firebase.yml
firebase.stage.appId / firebase.appId | Firebase App ID of the app that receives test builds (not secret) | gradle.properties | stage (single env: —) | Firebase console → Project settings → Your apps | app/build.gradle.kts (firebaseAppDistribution)

## External setup
Service | Setup | Action IDs
GitHub | Secrets (see Secrets & keys) and branch protection on main | SIGN-2, CI-1, CI-2
Google Play Console | App com.ilyassavli.helloworld, store listing, content rating, target audience, privacy policy, Data safety, Play App Signing, internal testing track | STORE-2, STORE-3
Firebase App Distribution | Tester group 'testers'; service account for CI | DIST-1

## Verify
Check | Command / steps
Quality gate | python3 tools/check_rules.py . && ./gradlew assembleDebug detekt ktlintCheck lint testDebugUnitTest testStageDebugUnitTest koverVerify
Release build (R8) | ./gradlew :app:bundleProdRelease (signed when KEYSTORE_* are set)
Stage app on a device | ./gradlew :app:installStageDebug
Refresh this checklist | python3 tools/handover_check.py
Local export | tools/export_build.sh --out <folder> --type apk --install

## Known exceptions
Source (SPEC.md) | Item
Known exceptions | Hello has no Route/ViewModel: the screen has no state, so HelloScreen is the entry's content (TASKS hello-6 dropped).
Known exceptions | Scaffold helpers a one-screen app doesn't use were deleted by the dead-code gate (state components, AppResult/AppError, dispatcher binding, navigateTo). core/common, core/model, core/ui and core/data stay as empty modules because the feature convention plugin and koverVerify expect them.
Known exceptions | Code review (E4): skipped "Timber planted but unused" (always-on by skill decision, OBS-01) and the scaffold-template root cause (skill change, recorded in the skill plan).